## Construction Gantt Chart
Gradution Project
Project: |  | Eye Tracking
Prof: |  | DR Aliaa
Construction Gantt Chart
Construction Activities |  |  | DURATION (Days)
START DATE | END DATE | DESCRIPTION
2024-09-16 | 2024-09-23 | literature review | 7
2024-09-24 | 2024-09-30 | tools for game | 6
2024-12-15 | 2025-01-01 | game | 16
2025-01-15 | 2025-02-01 | linking the game with machine learning | 16
2025-03-01 | 2025-03-20 | machine learning rehabilitation | 19
2025-03-22 | 2025-04-30 | make project more advanced | 38

## Useful Tips
USEFUL TIPS
1 | When enteringactivity start and end dates in columns "C" and "D" use the following date format: DD/MM/YYYY
2 | To change colour of fill and text in cells, use HOME -> FONT tool palette.
3 | To change the start date shown on the gantt chart: Fotmat -> (Current Selection tab) Format Selection -> Axis Options -> Bound: Minimum -> Change value to a number that will be appropriate for your project start date. e.g. 43831 = 1/1/2020 44197 = 1/1/2021 44562 = 1/1/2022 .....

## ©
© TemplateLab.com